## Assets
ID | Category | Item | Qty | Spec / Dimensions | Format | Milestone | Priority | Status | Notes
T-001 | Tiles | 萬 suit faces 1–9 | 9 | 96×128 pt design base; engraved glyph; export @1x/2x/3x atlas | PNG atlas (SVG master) | M3 | P0 | Not started | Traditional red/black glyphs
T-002 | Tiles | 筒 suit faces 1–9 | 9 | 96×128 pt; @1x/2x/3x | PNG atlas (SVG master) | M3 | P0 | Not started | Blue/black
T-003 | Tiles | 索 suit faces 1–9 | 9 | 96×128 pt; @1x/2x/3x | PNG atlas (SVG master) | M3 | P0 | Not started | Green; 1索 bird
T-004 | Tiles | Wind faces 東南西北 | 4 | 96×128 pt; @1x/2x/3x | PNG atlas (SVG master) | M3 | P0 | Not started
T-005 | Tiles | Dragon faces 中發白 | 3 | 96×128 pt; @1x/2x/3x | PNG atlas (SVG master) | M3 | P0 | Not started | 白 = blue frame
T-006 | Tiles | Flower faces 春夏秋冬梅蘭菊竹 | 8 | 96×128 pt; ornate but distinct silhouettes | PNG atlas (SVG master) | M3 | P0 | Not started
T-007 | Tiles | 百搭 joker face | 1 | 96×128 pt; gold 百搭 glyph + jade glow; must read at 40×54 river size | PNG atlas (SVG master) | M4 | P0 | Not started | GDD 01 §4
T-008 | Tiles | Tile back | 1 | 96×128 pt; 麻雀綠 lattice | PNG atlas | M3 | P0 | Not started
T-009 | Tiles | Tile side/edge chrome | 1 | 9-patch or per-size sprite | PNG | M3 | P1 | Not started | 3D-ish depth
T-010 | Tiles | Face-down wall pair sprite | 1 | stacked 2-tile unit for wall render | PNG atlas | M3 | P0 | Not started
E-001 | Table & props | Table frame + green inlay | 1 | per-aspect bg or 9-patch; rosewood #5C3A21 / inlay #2E5E4E | PNG | M3 | P0 | Not started
E-002 | Table & props | Room backdrop w/ neon dressing | 3 | layered PNGs, parallax-lite; low contrast | PNG | M5 | P2 | Not started | Non-play-area dressing
E-003 | Table & props | Center hub panel (拉牌盒 style) | 1 | square panel; holds 圈風/局數/牌數/骰 | PNG + widget | M3 | P0 | Not started
E-004 | Table & props | 莊 dealer coin | 1 | brass style, 64×64 | PNG | M3 | P0 | Not started
E-005 | Table & props | 拉莊 chip stack numerals 1–9 | 9 | red chips w/ 拉N numeral | PNG atlas | M3 | P1 | Not started
E-006 | Table & props | Dice faces + tumble animation | 1 | faces 1–6 + tumble sprite sheet ~600ms | PNG sheet | M3 | P0 | Not started | Used by 開門/執位/換牌
E-007 | Table & props | Seat wind chips 東南西北 | 4 | small chips beside avatars | PNG atlas | M3 | P0 | Not started
E-008 | Table & props | Seat frame / name plate | 1 | holds avatar+name+badges | PNG 9-patch | M3 | P0 | Not started
E-009 | Table & props | Status badges (AI robot, wifi-off, host crown) | 3 | 24–32 px | PNG atlas | M3 | P1 | Not started
E-010 | Table & props | Room-code card + QR frame | 1 | share screen hero card | PNG + widget | M5 | P1 | Not started
E-011 | Table & props | 叮 red corner tag | 1 | river-tile overlay tag | PNG | M3 | P0 | Not started
A-001 | Avatars | Player avatar set (茶餐廳 theme) | 14 | 128×128 round; 奶茶/菠蘿包/蛋撻/燒賣/貓店長/雀友… | PNG atlas | M5 | P1 | Not started | 12–16 target
A-002 | Avatars | AI mascot avatars | 4 | robot-ified variants of A-001 style | PNG atlas | M4 | P1 | Not started
U-001 | UI kit | Action pill buttons 食/碰/槓/上/叮/過 | 18 | 6 colorways × 3 states (normal/pressed/disabled); ≥64 px tall | PNG 9-patch/widget | M3 | P0 | Not started | Color coding per GDD 01 §8
U-002 | UI kit | Menu buttons primary/secondary | 6 | pill, neon border active | widget theme | M3 | P0 | Not started | Mostly Flutter theming
U-003 | UI kit | Form controls (toggle/stepper/slider/radio-card) | 4 | editor + wizard styling | widget theme | M4 | P0 | Not started
U-004 | UI kit | Countdown ring | 1 | draining ring; shader or sprite sheet | shader/sheet | M3 | P0 | Not started | Claim & turn timers
U-005 | UI kit | Dialog/sheet frames | 2 | dark card + gold rule line | PNG 9-patch | M3 | P0 | Not started
U-006 | UI kit | List cells (editor row, 圖鑑 card) | 2 | widget styling | widget theme | M4 | P0 | Not started
U-007 | UI kit | Rules summary chip | 1 | lobby/table diff-vs-official chip | widget | M4 | P1 | Not started
U-008 | UI kit | Ledger strip elements (chain link/broken/口 dot) | 3 | compact strip art | PNG atlas | M3 | P1 | Not started | 拉/踢半 UI
U-009 | UI kit | Line icon set | 30 | 2 px stroke, rounded; settings/share/sound/help/edit/save/replay/QR/exit/kick/fairness… | SVG→font/atlas | M3 | P1 | Not started
U-010 | UI kit | App fonts (Noto Sans TC + display face) | 2 | OFL check for display face; tnum digits | TTF/OTF | M3 | P0 | Not started | GDD 01 §3; license gate
V-001 | VFX | Deal sweep trail | 1 | 40 ms/tile stagger | engine FX | M3 | P1 | Not started
V-002 | VFX | Claim word flash cards 上/碰/槓/食/自摸/搶槓/雙響 | 7 | display-type card + neon burst | PNG + FX | M3 | P0 | Not started
V-003 | VFX | 叮 stamp effect | 1 | red stamp thunk ≤400 ms | sprite/FX | M3 | P0 | Not started
V-004 | VFX | Win fan-out glow + 番 row cascade | 1 | win overlay sequence | engine FX | M3 | P0 | Not started
V-005 | VFX | Gold count-up particles + brass tick sync | 1 | score总 count-up | engine FX | M3 | P1 | Not started
V-006 | VFX | Confetti (big win) | 1 | ≥100番 tier | engine FX | M4 | P2 | Not started
V-007 | VFX | Neon flicker overlay (超大糊) | 1 | 420番-class | engine FX | M4 | P2 | Not started
V-008 | VFX | 拉 chain link / 踢半 shatter | 2 | avatar-to-avatar ledger anim | sprite/FX | M3 | P1 | Not started
V-009 | VFX | 流局 wall-collapse | 1 | banner + collapse | engine FX | M3 | P1 | Not started
V-010 | VFX | Flower replace sparkle / 補花 flip | 1 |  | engine FX | M3 | P2 | Not started
V-011 | VFX | Turn glow ring + 過水 red flash | 2 | state cues | engine FX | M3 | P0 | Not started
AU-001 | Audio | Cantonese voice pack — male | 9 | 上/碰/槓/食/自摸/叮/搶槓/雙響/流局; <600 ms; −16 LUFS | OGG 44.1k | M5 | P0 | Not started | Record both packs same session
AU-002 | Audio | Cantonese voice pack — female | 9 | same script | OGG 44.1k | M5 | P0 | Not started
AU-003 | Audio | SFX set | 20 | tile clack×3, shuffle, wall build, discard, draw, dice, buttons, claim stinger, 叮 thunk, fanfare S/L, gong, brass tick, chain clink/shatter, 流局 sting, pop, error | OGG | M3–M5 | P0 | Not started | Foley-real preferred
AU-004 | Audio | BGM — lobby loop | 1 | lo-fi 港風, 60–90 s seamless | OGG | M5 | P2 | Not started
AU-005 | Audio | BGM — in-game loops | 2 | ducks under voice | OGG | M5 | P2 | Not started
D-001 | Data/content | fan_table.json (official 番種簡表) | 1 | ~150 entries; verified line-by-line vs 總例 PDF p.18; schema per GDD 03 §1 | JSON | M1 | P0 | Not started | GATE for everything
D-002 | Data/content | 圖鑑 example hands | 150 | per-番種 example hand as tile-list JSON | JSON | M4+ | P2 | Not started | Ship progressively
D-003 | Data/content | In-app rules reference text | 1 | own wording pending R1 rights decision | MD/JSON | M4 | P1 | Not started | Risk R1
D-004 | Data/content | Canned chat phrases | 12 | 快啲啦/好牌!/唔好意思/食得好… | JSON | M5 | P2 | Not started
D-005 | Data/content | Tutorial script (60-s interactive tour) | 1 | deal→claim→叮→win | JSON/code | M6 | P1 | Not started
D-006 | Data/content | Editor preview sample hand | 1 | fixed showcase hand | JSON | M4 | P1 | Not started
S-001 | Store | App icon | 1 | 512×512; ivory tile 「開」 neon glow | PNG | M6 | P0 | Not started
S-002 | Store | Feature graphic | 1 | 1024×500 | PNG | M6 | P0 | Not started
S-003 | Store | Screenshots | 8 | phone 16:9 & 20:9; table/win/editor/wizard/百搭/ledger/圖鑑/lobby + caption bands | PNG | M6 | P0 | Not started
S-004 | Store | Privacy policy page | 1 | hosted URL | web | M6 | P0 | Not started | Data-safety form dependency
S-005 | Store | Listing copy 繁中 | 1 | title/short/full desc; no gambling wording | text | M6 | P0 | Not started | Name TBD, check collisions
S-006 | Store | IARC questionnaire answers | 1 | simulated gambling = yes; no real money | doc | M6 | P0 | Not started

## Summary
Asset Production Summary
《開枱》港式台牌 — asset tracker · basis: game-design-doc/09-ASSETS.md · 2026-07-07
By category
Category | Line items | Unit qty | Done
Tiles | 10 | 46 | 0
Table & props | 11 | 26 | 0
Avatars | 2 | 18 | 0
UI kit | 10 | 69 | 0
VFX | 11 | 19 | 0
Audio | 5 | 41 | 0
Data/content | 6 | 166 | 0
Store | 6 | 13 | 0
TOTAL | 61 | 398 | 0
By priority
Priority | Line items
P0 | 37
P1 | 16
P2 | 8
By milestone
Milestone | Line items
M1 | 1
M3 | 34
M4 | 9
M4+ | 1
M5 | 8
M6 | 7
M3–M5 | 1